Annex III of UNEP/FAO/RC/CRC.19/14

Workplan for the preparation of draft decision guidance documents

|  |  |  |
| --- | --- | --- |
| *Tasks to be carried out* | *Responsible persons* | *Deadlines* |
| Draft an internal proposal based on the information available to the Committee | Chair  Drafter | 15 December 2023 |
| Send the draft internal proposal to the drafting group members for comments via email | Secretariat | 15 December 2023 |
| Replies | Drafting group members | 19 January 2024 |
| Update the internal proposal on the basis of comments from drafting group members | Chair  Drafter | 19 February 2024 |
| Send the updated internal proposal to the Committee members and observers for comments via email | Secretariat | 19 February 2024 |
| Replies | Committee members and observers | 19 March 2024 |
| Draft a decision guidance document on the basis of the comments of the Committee members and observers | Chair  Drafter | 15 April 2024 |
| Send the draft decision guidance document to the drafting group members for comments via email | Secretariat | 15 April 2024 |
| Replies | Drafting group members | 3 May 2024 |
| Finalize the draft decision guidance document on the basis of the comments of the drafting group members | Chair  Drafter | 24 May 2024 |
| Send the draft decision guidance document to the Secretariat | Chair  Drafter | 24 May 2024 |
| Submit the draft decision guidance document for consideration by the Committee at its twentieth meeting | Secretariat | 5 August 2024 |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |